## QAPI Plan FY25-26
Domain | Goal | Health Plan | Performance Indicators | Method for Assessment | Narrative | Baseline FY24-25 | Results FY25-26 | Responsible Team Primary/Secondary
Accessibility of Services (ACC) | 100% of calls will be appropriately connected. | Both | All calls will be appropriately connected (24/7 Access Line to utilize script) to a live person speaking the caller’s language (includes use of interpreter); results will be measured. | Quality Management Services (QMS) will conduct quarterly 24/7 Access Line Test Calls. Test call data and the QMS Test Call Summary Report will be reviewed and discussed quarterly in the ASO QI/QA meeting with QMS and Behavioral Health Plan (BHP) - Inpatient Program. | QMS is responsible for completing quarterly test calls to monitor the 24/7 Access Line. A report is completed and discussed with the ASO during the quarterly ASO QI/QA meeting. | 100% (50/50 callers were connected to a live person speaking their language. 20/50 calls were in English while the remaining 30 calls were conducted in OC threshold languages (Vietnamese, Farsi, Spanish, Mandarin, Korean). |  | Inpatient Designation Support Services (IDSS)
Accessibility of Services (ACC) | 95% of telephone calls (including after hours calls) will be answered within 30-seconds. | SMHS | Specialty Mental Health Services (SMHS), 24/7 Access Line, managed by the ASO, will answer at least 95% of telephone calls (including after hours calls) within 30-seconds. | Call data will be reviewed and discussed monthly at the ASO Program meeting and quarterly in the ASO QI/QA meeting with QMS. | The BHP currently contracts with Carelon as the BHP ASO to managed the 24/7 Access Line. The ASO logs all call and provides this data to the BHP monthly. | 95% of calls answered in 30 seconds for BHP-related calls. |  | Data Analytics and Evaluation (DAE) / IDSS
Accessibility of Services (ACC) | 95% of telephone calls (including after hours calls) will be answered within 30-seconds. | DMC-ODS | The DMC-ODS, 24/7 Access Line, managed by the ASO will answer at least 95% of telephone calls (including after hours calls) within 30 seconds. Report to be provided at least annually. | Call data will be reviewed and discussed monthly at the ASO Program meeting and quarterly in the ASO QI/QA meeting with QMS. | QMS is responsible for completing quarterly test calls to monitor the 24/7 Access Line. A report is completed and discussed with the ASO during the quarterly ASO QI/QA meeting. | 95% of calls answered in 30 seconds for DMC-ODS-related calls. |  | DAE / IDSS
Accessibility of Services (ACC) | Ensure timely access for initial appointment requests for all routine outpatient SMHS, at least 80% of the time. | SMHS | SMHS members with an initial request for routine outpatient services shall be offered an appointment within 10 business days. | Monthly data review of the Electronic Health Record (EHR) Access Log by MCST. Access Log data to be reviewed at least annually with the Community Quality Improvement Committee (CQIC). | Timely Access is monitored by use of an access log within the Integrated Records Information System (IRIS) EHR system for all points of access. This log captures the date of the initial request for SMHS treatment services by Medi-Cal members, as well as the date/time of the offered appointment. To facilitate timely access to routine outpatient services, Data Analytics and Evaluation (DAE) team will review the access log report at least monthly. QMS Managed Care Support Team (MCST) to assist in the monitoring and working with SMHS program administrators and providers to verify and confirm access log data. All access log data will be confirmed quarterly and reviewed at least annually with the CQIC. | Adults: 95% of adult clients offered an outpatient appointment within 10 business days. Children: ~100% of children clients were offered an outpatient appointment within 10 business days. |  | DAE / Managed Care Support Team (MCST)
Accessibility of Services (ACC) | Ensure timely access for initial appointment requests for all urgent SMHS, at least 80% of the time. | SMHS | SMHS members with an initial request for urgent services will be offered an appointment within 48 hours of contact (2 calendar days). | Monthly data review of the EHR Access Log by MCST. Access Log data to be reviewed at least annually with the CQIC. | Timely Access is monitored by use of an access log within the IRIS EHR system for all points of access. This log captures the date of the initial request for urgent services by Medi-Cal members, as well as the date/time of the offered appointment. To facilitate timely access to urgent outpatient services, Data Analytics and Evaluation (DAE) team will review the access log report at least monthly. QMS MCST to assist in the monitoring and working with SMHS program administrators and providers to verify and confirm access log data. All access log data will be confirmed quarterly and reviewed at least annually with the CQIC. | Adults: 96% of adult clients offered an urgent appt within 2 calendar days. Children: 85% of children clients were offered an urgent appointment within 2 calendar days. |  | DAE / MCST
Accessibility of Services (ACC) | Ensure timely access to all appropriate DMC-ODS Residential Treatment Services, at least 80% of the time. | DMC-ODS | DMC-ODS members with a request for Residential Treatment Services that is appropriate, per the ASAM based assessment, shall be offered a placement within 10 business days. | Monthly data review of the EHR Access Log by MCST. Access Log data to be reviewed at least annually with the CQIC. | Timely Access is monitored by use of an access log within the IRIS EHR system for all points of access. This log captures the date of the initial request for DMC-ODS treatment services by Medi-Cal members, as well as the date/time of the offered appointment. To facilitate timely access to Residential Treatment Services, the DAE team will review the access log report at least monthly. QMS MCST to assist in the monitoring and working with DMC-ODS program administrators and providers to verify and confirm access log data. All access log data will be confirmed quarterly, and reviewed at least annually with the CQIC. | 100% were offered an appt in 10 business days for both adult clients (n=651) and youth clients (n=13) requesting residential treatment services. |  | DAE / MCST
Accessibility of Services (ACC) | Ensure timely access for all initial requests to DMC-ODS Narcotic Treatment Service, at least 80% of the time. | DMC-ODS | DMC-ODS members with an initial request for Narcotic Treatment Services (NTP) shall be offered an appointment within 3 calendar days. | Monthly data review of the EHR Access Log by MCST. Access Log data to be reviewed at least annually with the CQIC. | Timely Access is monitored by use of an access log within the IRIS EHR system for all points of access. This log captures the date of the initial request for DMC-ODS treatment services by Medi-Cal members, as well as the date/time of the offered appointment. To facilitate timely access to Narcotic Treatment Services, the DAE team will review the access log report at least monthly. MCST to assist in the monitoring and working with DMC-ODS program administrators and providers to verify and confirm access log data. All access log data will be confirmed quarterly, and reviewed at least annually with the CQIC. | 100% of both adult clients (n=1,272) and youth clients (n=5) were offered an NTP/OTP appt within 3 business days. |  | DAE / MCST
Accessibility of Services (ACC) | Ensure timely access for initial appointment requests for outpatient DMC-ODS services, at least 80% of the time. | DMC-ODS | DMC-ODS members with an initial request for outpatient services that is appropriate, per the ASAM, based assessment shall be offered an appointment within 10 calendar days. | Monthly data review of the EHR Access Log by MCST. Access Log data to be reviewed at least annually with the CQIC. | Timely Access is monitored by use of an access log within the IRIS EHR system for all points of access. This log captures the date of the initial request for DMC-ODS treatment services by Medi-Cal members, as well as the date/time of the offered appointment. To facilitate timely access to routine outpatient services, the DAE team will review the access log report at least monthly. MCST to assist in the monitoring and working with DMC-ODS program administrators and providers to verify and confirm access log data. All access log data will be confirmed quarterly, and reviewed at least annually with the CQIC. | 98% (n=3224) of adult clients and 88% (n=112) of youth clients were offered an outpatient appt within 10 business days. |  | DAE / MCST
Accessibility of Services (ACC) | Increase participation in appropriate treatment services in conjunction with Narcotic/Opioid Treatment Program (NTP/OTP) services for improved treatment outcomes. | DMC-ODS | Cases with a second admission to Narcotic Treatment Program (NTP) services within 60 days without any other services will be identified and submitted for utilization review to provide treatment engagement recommendations. | 25% of re-admissions will be reviewed. | Medi-Cal members who present for a second NTP admission within 60 days may be at higher risk for leaving treatment prematurely or unsuccessfully. By providing additional review strategies, it is expected that linkage to an appropriate level of care will be more likely to sustain long term stability. Medi-Cal members who do not successfully link to an appropriate level of care along with NTP services are less likely to develop mechanisms to maintain long term sobriety without reliance on NTP services only. Supporting members upon the second admission will provide a mechanisms for increasing access and utilization of additional treatment. | This goal was not met for FY24-25 No UR activities were offered to these clients as our data was not available in real time to identify these episodes as they occurred. In the past year, a Utilization Management and Complex Care Coordination (UMCC) team was established to enable more timely UR activities. A DAE function area has also increased data analytics capabilities which are expected to be able to support automation of data to identify the target population for this metric. |  | DAE / QI Support
Accessibility of Services (ACC) | Implementation of OCHCA as a provider of Enhanced Care Management (ECM) for the MCP and communication of the MCP Community Supports (CS) benefit | Both | Establish a process for OCHCA to accept ECM referrals from the health plan. Communicate CS options available to OCHCA health plan eligible members. | QMS staff will collaborate with the MCP, CalOptima, to establish a mechanism for identifying OCHCA health plans members who are eligible for ECM once referred for services. QMS staff will collaborate with the MCP to identify CS resources that could be made available to OCHCA health plan eligible members. Ongoing collaborations will take place between QMS staff and the MCP to ensure ongoing coordination of services. | As part of CalAIM, Enhanced Care Management (ECM) and Community Support (CS) services have been made available to eligible Medi-Cal members in order to support their care and clinical services they receive. ECM and CS are health plan benefits intended to strengthen the effectiveness of medical and clinical care provided to members. OCHCA has opted to become an ECM provider for the MCP, CalOptima, for the purposes of making ECM available to County health plans eligible members who would not receive this level of care coordination otherwise. As such, this service is limited to those BHP programs that would be more likely to utilize this additional benefit. Most SMHS and DMC-ODS programs already offer routine Care Coordination that meets or exceeds the ECM standards, which would make accessing the ECM benefit duplicative in most programs. OCHCA will continue to collaborate with the MCP to identify opportunities for offering ECM to members when care coordination through the SMHS or DMC-ODS is not already available. | Effective referral mechanisms have been established between CalOptima Health and the county BHP. There are no agreements in place between Orange BHP and Kaiser Permanente as of the end of this FY. This goal will be carried over to FY25-26 to determine if ECM and CS agreements between KP and Orange BHP will be established. |  | CalAIM
Safety of Services / Clinical Care (SCC) | To monitor the safety and effectiveness of medication practices in SMHS programs. To improve data quality for Medication Monitoring. | SMHS | Percentages that key indicators identified in each monitoring period are found on the records. 1. Are psychiatric diagnoses clearly documented and supported in the last 12 months? 2. Are vital signs, laboratory, and metabolic data regularly considered and documented? 3. Is there documentation in the chart of care coordination with the PCP? 4. Do all prescribed medications have a medication consent form with all fields completed? 5. If psychotropic medications are being prescribed, are these appropriate for the documented diagnoses? 6. If the use of off-label medication or polypharmacy is noted, is there a rationale documented in the chart? 7. If controlled substances are being prescribed, was CURES checked? 8. If psychotropic medications are being prescribed, is there documentation that the client was asked about side effects? | All completed medication monitoring forms to be submitted annually each FY. Summary data reported and discussed annually at CQIC. The Medication Monitoring review is based on peer-review of charted psychiatric notes. The review includes items such as whether diagnosis is reviewed and updated, whether labs performed, and response to treatment. Medication prescribing practices will be reviewed via the Medication Monitoring Process throughout the year by Associate Medical Directors in each Division. The CQIC and/or SMHS QI coordinators workgroup shall review and discuss the medication monitoring activities and shall make any recommendations deemed needed. | SMHS will work to improve data quality for Medication Monitoring. To accomplish this, each Division will submit their completed Medication Monitoring Forms by the end of April within the current fiscal year. Annual reports summarizing the results will be completed and reviewed at CQIC and discussed as appropriate in meetings with the Behavioral Health Services (BHS) Medical Director. Medication monitoring review is implemented as a mechanism to monitor the safety and effectiveness of medication practices. The monitoring mechanism shall be under the supervision of a person licensed to prescribe or dispense prescription drugs. Monitoring shall occur at least annually. The medication monitoring occurs under the oversight of the DMC-ODS Medical Director in collaboration with the QMS QI Systems Team. This process is the mechanism to monitor appropriate and timely intervention of occurrences that raise quality of care concerns. Appropriate follow-up action shall be taken when such an occurrence is identified. The results of the intervention shall be evaluated by the Contractor at least annually. | Chi-square analyses were conducted to compare "yes" responses in FY 24/25. Adults: n=401. Children: n=164 1. Adults: 99.2%; Same as the previous FY. Children: 91.7%; A statistically significant decrease from the previous FY. 2. Adults: 79.3%; Similar to the previous FY. Children: 72.7%; A small decrease from the previous FY. 3. Adults: 85.7%; A small decrease from the previous FY. Children: 83.9%; An increase from the previous FY. 4. Adults: 89.5%; A small increase from last FY. Children: 86.6%; Similar to the previous FY. 5. Adults: 98.2%; A statistically significant increase from the previous FY (p<0.01). Children: 95.1%; A small decrease from the previous FY. 6. Adults: 85.9%; An improvement over the previous FY. Children: 88.6%; Similar to last FY. 7. Adults: 57.6%; A statistically significant decrease compared to the previous FY (p<0.01). Children: 76.2%; A statistically significant improvement over the previous FY. 8. Adults: 96.0%; A statistically significant decrease from last FY (p<0.05). Children: 92.4%; A small decrease from last FY. |  | DAE / QI Support
Safety of Services / Clinical Care (SCC) | To monitor the safety and effectiveness of medication practices for SUD programs. To improve data quality for Medication Monitoring. | DMC-ODS | Percentages that key indicators identified in each monitoring period are found on the records. 1. Diagnosis affirmed or changed? 2. Client participation in other treatment elements? 3. Coordination of care? 4. Medical conditions considered? 5. All meds have consent form completed? 6. Medications contribute to abstinence? 7. Naloxone accessible? 8. Dual Diagnosis considered in treatment plan? | All completed medication monitoring forms to be submitted annually each FY. Summary data reported and discussed annually at CQIC. The Medication Monitoring review is based on peer-review of charted psychiatric/physician notes. The review includes items such as whether diagnosis is reviewed and updated, whether labs performed, and response to treatment. Medication prescribing practices will be reviewed via the Medication Monitoring Process throughout the year by Associate Medical Directors in SUD. The CQIC and/or SUD QI coordinators workgroup shall review and discuss the medication monitoring activities for the and shall make any recommendations deemed needed. | The DMC-ODS will work to improve data quality for Medication Monitoring. To accomplish this, SUD programs will submit their completed Medication Monitoring Forms by the end of April within the current fiscal year. Annual reports summarizing the results will be completed and reviewed at CQIC and discussed as appropriate in meetings with the BHS Medical Director. Medication monitoring review is implemented as a mechanism to monitor the safety and effectiveness of medication practices. The monitoring mechanism shall be under the supervision of a person licensed to prescribe or dispense prescription drugs. Monitoring shall occur at least annually. The medication monitoring occurs under the oversight of the DMC-ODS Medical Director in collaboration with the QMS QI Systems Team. This process is the mechanism to monitor appropriate and timely intervention of occurrences that raise quality of care concerns. Appropriate follow-up action shall be taken when such an occurrence is identified. The results of the intervention shall be evaluated by the Contractor at least annually. | DMC Medication Monitoring results were presented by DA&E on 10/23/2025. Below are the percentage of 'Yes' responses. 1. Diagnosis charted and supported by DSM-V? 98% (FY24/25) vs. 100% (FY23/24). 2. Client participation in other treatment elements? 99% vs. 100%. 3. Coordination of care? 87% vs. 78%. 4. Medical conditions considered? 96% vs. 89%. 5. Rx have consent form completed? 86% vs. 94%. 6. (A newly revised item in FY 24/25) CURE documentation? 88%. 7. Naloxone accessible? 88% vs. 90%. 8. Co-occurring mental health conditions considered? 90% vs. 85%. There were no statistically significant findings between the two FYs. |  | DAE / QI Support
Safety of Services / Clinical Care (SCC) | Continuity of Care requests are to be review and timely notification provided, 100% of the time. | Both | Number of Continuity of Care (COC) requests received by each plan. Percentage of time each COC is reviewed and processed within established timeliness, including required notifications | All BHP County and Contracted provides are to submit any Continuity of Care requests to QMS immediately. QMS will receive, track, review and approve/deny any Continuity of Care requests. QMS to provide data to DAE for NACT reporting to DHCS. All BHP COC requests are received, reviewed, tracked and approved/denied by QMS. Information is tracked in a spreadsheet with all DHCS required fields. COC data is report for NACT submission annually. | QMS developed a BHP centralized process for all COC requests by members. This process is monitored by the QMS managers and approval for any COC requests is communicate to program. All BHP County and Contracted provides are to submit any Continuity of Care requests to QMS immediately. QMS will receive, track, review and approve/deny any Continuity of Care requests. QMS to provide data to DAE for NACT reporting to DHCS. | The plan received zero(0) Continuity of Care requests in FY 24-25 |  | Utilization Management & Complex Care Coordination (UMCCC)
Safety of Services / Clinical Care (SCC) | Ensure compliance with Physical Exam requirements for members receiving SUD services through the DMC-ODS. | DMC-ODS | Member records shall evidence that members have obtained a physical examination in the past twelve months or alternatively have a treatment goals to obtain a physical exam during the course of treatment. 100% for reviewed records. | Upon clinical records reviews by the Clinical Records Review (CRR) team, this measure will be tracked through the "Chart review" tool, which contains an item for capturing yes/not for this items being present in each record reviewed. This data is compiled for all reviewed providers, to result in a percentage of compliant records. | If a member had a physical examination within the twelve-month period prior to the member's admission to treatment date, the physician or registered nurse practitioner or physician’s assistant (physician extenders) shall review documentation of the member's most recent physical examination within 30 calendar days of the member's admission to treatment date. If a provider is unable to obtain documentation of a member's most recent physical examination, the provider shall describe the efforts made to obtain this documentation in the member's individual patient record. | FY 24-25 Clinical Records Review showed that documentation of the physical examination requirement was found in 88.61% of the records. This is an improvement from FY 23-24, where it was reported in 78.15% of the records. |  | DAE / Clinical Records Review Team (CRRT)
Safety of Services / Clinical Care (SCC) | Ensure that coordination with physical health care is taking place for members. | DMC-ODS | Member records shall evidence that coordination with physical health providers and resources is taking place during the course of treatment. 100% for reviewed records. | Upon clinical records reviews by the CRR team, this measure will be tracked through the "Chart review" tool, which contains an item for capturing yes/not for this items being present in each record reviewed. This data is compiled for all reviewed providers, to result in a percentage of compliant records. | DMC-ODS shall ensure continuity and coordination of care with physical health care providers. DMC-ODS shall coordinate with other human services agencies used by its members. | FY 24-25 Clinical Records Review showed that documentation of the coordination with physical health was found in 91.79% of the records. This represents a slight decrease compared to FY 23-24, where it was reported in 92.95% of the records. |  | DAE / CRRT
Safety of Services / Clinical Care (SCC) | Ensure that Evidence Based Practices (EBP) are used in the delivery of DMC-ODS covered services. | DMC-ODS | Member records shall evidence the use of EBP during the course of treatment. 100% of reviewed records. | Upon clinical records reviews by the CRR team, this measure will be tracked through the "Chart review" tool, which contains an item for capturing yes/not for this items being present in each record reviewed. This data is compiled for all reviewed providers, to result in a percentage of compliant records. | Providers will implement at least two of the following EBPs. The two EBPs are per provider per service modality. DMC-ODS will ensure the providers have implemented EBPs and regular training of EBPs to staff during reviews. The required EBPs include: a. Motivational Interviewing b. Cognitive-Behavioral Therapy c. Relapse Prevention d. Trauma-Informed Treatment e. Psycho-Education One of the EBP shall be Motivational Interviewing for all providers. | FY 24-25 Clinical Records Review showed that documentation of use of EBP was found in 99.84% of the records. This is an improvement compared to FY 23-24, where it was reported in 94.89% of the records. |  | DAE / CRRT
Safety of Services / Clinical Care (SCC) | Increase utilization of EBPs by the BHP in alignment with Behavioral Health Services Act (BHSA) and Behavioral Health Community-based Organized Networks of Equitable Care and Treatment (BH-CONNECT). | Both | In preparation for July 1, 2026 implementation, the BHP will engage with DHCS identified Centers of Excellence (COE). | Attend at least one consultation meeting with each COE by June 30, 2026. | BHSA and BH-CONNECT have identified the following EBPs: Functional Family Therapy (FFT), Multisystemic Therapy (MST), Parent-Child Interaction Therapy (PCIT), High Fidelity Wraparound (HFW), Assertive Community Treatment (ACT), Forensic Assertive Community Treatment (FACT), Individual Placement Support (IPS) Supported Employment, Coordinated Specialty Care for First-Episode Psychosis (CSC for FEP). | This is a new goal. |  | Quality Standards & Clinical Practice (QSCP)
Member Satisfaction (MS) | Administer SMHS annual consumer perception surveys for current fiscal year and provide results of the previous fiscal year. | SMHS | 1) State-mandated SMHS consumer perception surveys (CPS) will be administered at the SMHS County and Contract Provider locations as required by the state. 2) Reducing the percentage of surveys returned late or invalid. | Successful competition of CPS administration and submission SMHS will continue efforts towards decreasing the percentage of surveys returned incomplete and past the submission deadline. | Annual surveys will be conducted to collect data for reporting on the federally determined National Outcome Measures (NOMs). QMS will coordinate the distribution and collection of all surveys for submission to DHCS as required. Ongoing efforts will be made to determine interventions to decrease incomplete or late submissions. Additionally, satisfaction and effectiveness of services will be evaluated and shared with the CQIC. | The CPS was administered in May 2025 and surveys collected by all reporting units were batched and sent to Data Analytics Staff to review, verify, and sent to UCLA (the DHCS CPS Coordination Team) for processing by mid-June 2025. Youth: A total of 1,016 surveys were distributed, with 873 completed, resulting in an overall completion rate of 85.9%, with high scores in cultural sensitivity (4.4) and general satisfaction (4.3). Domains for improvement included outcome (3.9) and functioning (3.9). Family: A total of 1,448 surveys were distributed, with 1,297 completed, resulting in an overall completion rate of 89.6%, with high scores in cultural sensitivity (4.6). Domains for improvement included outcome (3.9) and functioning (4.0). Adults A total of 1,911 surveys were distributed, with 1,142 completed, resulting in an overall completion rate of 59.8%. The average general satisfaction score was 4.5, with high scores (4.4) in Access, Participation, and Quality. All outcomes measures were at or above 4.0. Older Adults: A total of 155 surveys were distributed, with 153 completed, resulting in an overall completion rate of 98.7%. All measures were at or above the agree level 4.0, with high scores in general satisfaction (4.5) and Access and Quality at 4.4. |  | DAE / QI Support
Member Satisfaction (MS) | Administer treatment perception surveys (TPS) for current fiscal year and provide results of the previous fiscal year. | DMC-ODS | State-mandated DMC-ODS treatment perception surveys will be administered at the DMC-ODS County and Contract Provider locations as required by the state. Feedback will be given to the CQIC and to the service providers. | Completion of TPS administration and submission. Review data with providers at least annually. | QMS staff will coordinate the distribution, collection and submission of the TPS developed by the University of California, Los Angeles (UCLA) as part of the evaluation of the DMC-ODS as required by the Centers of Medicaid and Medicare. The DAE team will continue to evaluate data and report trends annually to DMC-ODS providers and the CQIC annually. | The survey was administered during a one-week period in the Fall to clients receiving DMC-ODS services. The findings below are based on responses collected from October, 2024, during which all clients attending services were invited to participate. In 2024, 1,012 surveys were collected for adults, and 14 were collected for youth. This is an increase from the previous fiscal year for adults. Youth data was not analyzed due to the small number of participants. Adults: The average score for each domain remains high (mean score above 4.0). The average overall score was 4.5, with high scores in Quality (4.6) and General Satisfaction (4.6). An area for improvement included Care Coordination (4.3). Statistically significant increases from 2023 were observed on the Outcome and General Satisfaction domains. Scores were slightly higher than Statewide for all domains, except for Care Coordination, which received the same score. Average TPS scores were higher among females, clients aged 65 and older, and those utilizing almost all to all telehealth services. Only 7% of respondents reported using telehealth for 'almost all' or 'all' of their services. Among those who used telehealth, 42% found it helpful. |  | DAE / QI Support
Member Satisfaction (MS) | Review all "Request for Change of Provider" Quarterly logs from all BHP programs to identify patterns and trends, conduct a root cause analysis on any identified patterns, and develop QI strategies, as needed, to address potential root causes underlying member requests for a change in provider. | Both | Data collected by MCST will be reviewed quarterly at the Divisional or CQIC meeting and will include at least the following items: 1) The number of requests, 2) The types of issues leading to change requests, 3) Any change requests that may reflect systems issues, 4) An assessment of the quality of the Divisions' response to the change requests. | BHP members request a change of provider through the clinic client representative. The program representative evaluates the request and, if appropriate, approves the request for a change of provider. BHP programs provide MCST with quarterly logs on change of provider. All data from the logs is to be entered into IRIS by program. MCST reconciles the quarterly logs with the data in IRIS to ensure accuracy. MCST to update spreadsheet on Provider Change Requests from all BHP programs and data provided to the DAE team for annual reporting. 1) Requests by members for a Change of Provider will be handled through the appropriate Service Chief and Program Director, who will report such requests. 2)A quarterly “Request for Change of Provider” log will be submitted to MCST. 3)The log will specify the name of the client, date, nature of the request, and the outcome of the request including the date of the therapist change. | Quarterly Change of Provider Log sheets for BHP were revised and standardized in Dec 2020. All quarterly logs are submitted to MCST by the BHP program on the 10th of the month subsequent to the quarter’s end. The MCST leads send regular, quarterly, reminders to the BHP programs to submit the Change of Provider. MCST reviews the Change of Provider logs and reconciles them with the IRIS Report and Grievance Tracking log. MCST provides a final copy of the programs logs and spreadsheet summarizing data from all programs to the DAE team. MCST also provides several trainings/reminders throughout the year about the Change of Providers to individual programs and at County and County-Contracted Clinics at monthly/quarterly meetings. MCST also provides monthly reminders on the SMHS Quality Review (QR) Tips and SUD Newsletters to highlight trends and updates. Data is reviewed at least annually at the CQIC. | FY 24/25 results were presented in the October 2025 CQIC meeting. The number of requests for Change of Provider/Second Opinion by service area (AOA, CYS and DMC-ODC), trends over time (last 8 quarters), and type of requests for AOA and CYS were shared. The number of requests for Change of Provider/Second Opinion for AOA (n=218) and CYS (n=116) services were slightly lower than the previous FY. For DMC services, 23 change of provider/2nd opinion requests were made, compared to 14 in the previous FY. Further investigation of the request type revealed that, for adults, the majority of the requests were due to the Care Treatment Given (46%), followed by Gender Differences (16%), Personality Differences (15%) and Schedules (7%). These trends are similar to the previous FY. For youth, most requests were made due to the Care Treatment Given (29%) and Personality Differences (28%), followed by Gender Differences (16%) and Schedules (13%). These trends are similar to the previous FY. Note: Care Treatment and Treatment Approach were provided using a combined category starting in FY 24-25, Q2. Based on the results, no trends or patterns signaling quality of care or system issues related to requests for change of provider were identified this year requiring further intervention. Starting in FY25-26, second opinion requests will be removed from the change of provider dataset as these items are indicators of different measures. |  | DAE / MCST
Member Satisfaction (MS) | Administer and report on member satisfaction with 24/7 Access Line network provider services, with callers reporting an average rating of at least 4 out of 5 on a Likert scale indicating satisfaction with the referral process. | Both | An average of 4 out of 5 on the Likert scale for satisfaction with outcomes will be observed from all callers to the 24/7 Access Line. | The ASO will assess the satisfaction of members receiving services at least annually, and report this data and any findings and recommendations at the joint ASO-BHP QI meeting. Completion of member satisfaction surveys. Review data with BHP at quarterly QI meeting. Results will be reviewed and discussed by the CQIC at least annually. | The BHP ASO is responsible for assessing the satisfaction of members receiving services at least annually. The data and findings are reviewed and discussed during the joint ASO-BHP QI meeting. These surveys will be conducted in the threshold languages. Results will be reviewed and discussed by the CQIC at least annually. | In 24/25 308 surveys collected (previous year n= 251) The post-call survey asked participants to rate their level of agreement on a 5-point rating scale (1-Strongly Disagree to 5-Strongly Agree). The post-call survey results are reported as an average score, with the mean score of 4.3. This indicates that participants responded with 'agree' regarding their satisfaction with the calling experience. |  | DAE / IDSS
Member Satisfaction (MS) | All grievance/appeals/State Fair hearings will be tracked on the QMS master spreadsheet with all DHCS required data fields. The spreadsheet will be audited at least quarterly to ensure compliance and accuracy of data; identify whether any patterns and trends exist in the data; conduct a root cause analysis on any identified patterns; and develop QI strategies, as needed, to address potential root causes underlying grievances, appeals and/or State Hearings. All data will be reviewed at least annually and the state required ABGAR/MCPAR submitted on time with no errors. | Both | Grievance data collected by QMS will be reviewed, at minimum annually with both the SMHS and DMC-ODS Administrators and will be reviewed annually at the CQIC to identify trends and QI opportunities, if any. The review will include at least the following items: 1) The number of grievances and fair hearings (including expedited) received, 2) The types of issues leading to grievances and fair hearings, 3) Any grievances or fair hearings that may reflect systems issues, 4) Appeals, 5) Expedited appeals 6) Grievance trends and issues. | MCST maintains a master spreadsheet for the fiscal year to collect the required DHCS data fields within 24 hours of receiving the initial grievance, appeals and state fair hearings. MCST conducts quarterly audits utilizing a monitoring tool that was developed to ensure grievances are entered correctly and investigated by the investigators. The master grievance/appeals/State Fair hearing tracking spreadsheets are reviewed for accuracy. DAE runs a quarterly report of repeated grievances to determine if a program and/or provider will need to be placed on a Corrective Action Plan to improve the quality of care and services. | MCST developed a quarterly monitoring tool to ensure the quality of the data collection and investigation process. The tool is used on a random sample of grievances and appeals to assess their accuracy and address any errors. The quarterly monitoring tools provide insight into trends that can be discussed with programs. These may include reminders, trainings, corrective action plans, etc. The MCST Grievance Leads review the grievance logs daily to ensure entry accuracy. They educate MCST staff with reminders, update and discuss new workflow processes and provide updates during weekly staff meetings. MCST also provides several trainings/reminders throughout the year about grievance/appeals/state fair hearings to individual programs and at County and County-Contracted Clinics at monthly/quarterly meetings. MCST also provides monthly reminders on the SMHS QR Tips and SUD Newsletters to highlight trends and updates. Data is reviewed at least annually at the CQIC. | Each quarter, the QMS & Data Analytics Team analyzed the data collected as part of the Annual MCPAR, Quarterly CalAIM Section 1914(b), and reports the number of grievances, appeals, and fair hearings to members of CQIC. Grievances by service area: AOA, CYS, and DMC had an increase in grievances in FY24/25 (AOA: n=200, CYS: n=87, DMC: n=58) compared to in FY23/24. Grievances by category: For both MHP and DMC-ODS services, the majority of grievances related to the quality of care received (MHP: n=229; DMC: n=42). Outcomes of grievances: For the MHP, the majority of the grievances resulted in Resolved within 24 hours (43%). Resolved within 24 hours indicates that the grievance is exempt (closed within 24 hours) and an investigation is not conducted. Such cases are mainly due to requests where the change is done immediately or within the same day. Another 23% of grievances were Unsubstantiated, while 5% were Substantiated. For DMC, 10% were Substantiated, the most common outcome of the grievance investigations was Unsubstantiated (38%), followed by Resolved within 24 hours (24%), and Inability to contact (16%). Appeals: In FY 24/25, AOA had 1 appeal; DMC-ODC had 2 appeals, which were all upheld. Fair hearings: MHP had 1 fair hearing request (dismissed); DMC-ODS had no fair hearing requests. |  | DAE / MCST
Quality Assurance (QA) | NOABDs are to be issued as required to members. Tracking and review of NOABDs is to occur by the MCST. NOABD data is to be reviewed quarterly to identify whether patterns or trends exist, conduct a root cause analysis on any identified patterns, and develop QI strategies, as needed, to address potential root causes underlying NOABDs. | Both | Appropriate issuing of NOABDs for the SMHS and DMC-ODS Plans, per MHSUD Information Notice NO: IN18-010E, IN25-015 and IN25-014 for every applicable determination. | MCST is to gather, track and monitoring the issuing of NOABDs. DAE extracts NOABD related data from IRIS. DAE collects additional NOABD data from MCST contained in the NOABD master spreadsheet. Data and trends to be reviewed at least annually at the CQIC. | All NOABDs issued by SMHS and DMC-ODS providers are to be sent to the MCST for review. The NOABD information is gathered, tracked and monitored in a NOABD master spreadsheet sheet. DAE is the lead in collecting, analyzing and presenting the NOABD data. They accomplish this by reviewing the data from IRIS and NOABD master spreadsheet. Their analysis is summarized and presented at the quarterly CQIC meeting. | The overall number of NOABDs issued across all programs decreased in FY 24/25 (n=13,674) compared to FY 23/24 (n=16,465). For AOA services, the number of NOABDs in FY 24/25 (n=5,957) was similar to FY 23/24 (n=6,006). The largest NOABD category was Termination (n=3,503), with Timely Access (n=2,116) the second largest. Most NOABDs remained steady across the four quarters. Timely Access NOABDs were lower in the last two quarters of the FY, compared to the first two quarters. For CYS services, the number of NOABDs issued in FY 24/25 (n=3,581) decreased from FY 23/24 (n=6,086). NOABDs were mainly issued because of Termination (n=3,017), followed by Delivery System (416). No notable trends were observed. For DMC services, the number of NOABDs issued in FY 24/25 (n=4,034) was similar to FY 23/24 (n=4,096). NOABDs were mainly issued because of Termination (n=3,931), followed by Timely Access (71). There was a decreasing trend in Timely Access NOABDs across the four quarters. For Inpatient Services, a decrease in NOABDs was observed in FY 24/25 (n=102) compared to FY 23/24 (n=277) and were mainly due to Payment denial (n=66). |  | DAE / MCST
Quality Assurance (QA) | Maintain DMC-ODS certification of county operated programs at all time in compliance with DCHS Provider Enrollment Division (PED). | DMC-ODS | Valid DMC-ODS Certification at all times. | Subject to DHCS provider enrollment certification requirements, the plan shall maintain continuous availability and accessibility of covered services and facilities, service sites, and personnel to provide the covered services through use of DMC-ODS enrolled providers. | Subject to DHCS provider enrollment certification requirements, the plan shall maintain continuous availability and accessibility of covered services and facilities, service sites, and personnel to provide the covered services through use of DMC-ODS enrolled providers. Such services shall not be limited due to budgetary constraints. The BHP shall notify PED of an addition or change of information in a providers pending DMC-ODS certification application within 35 days of receiving notification from the provider – for County operated programs. The BHP shall ensure that a new DMC-ODS certification application is submitted to PED reflecting the change for county operated programs. The BHP shall be responsible for ensuring that any reduction of covered services or relocations by county operated providers are not implemented until the approval is issued by DHCS. Within 35 days of receiving notification of a county operated provider’s intent to reduce covered services or relocate, the BHP shall submit, a DMC-ODS certification application to PED. The DMC-ODS certification application shall be submitted to PED 60 days prior to the desired effective date of the reduction of covered services or relocation. However, based on PED direction, the BHP is to submit SCA forms upon relocation and not sooner and PED reports having up to 180 days to complete the process. The BHP will continue to follow DHCS guidance for this item. All DMC-ODS enrolled providers shall be subject to continuing certification requirements at least once every five years upon notification of expiration by DHCS. | DMC certification was maintained at all County operated certified sites. No notifications of certification renewal were issued by DHCS to county operated programs. Upon inquiry, QM staff was informed that no action is needed by certified programs until a notice of renewal is issued by DHCS. This represents delay in certification timelines, unrelated to County factors. |  | Certification
Quality Assurance (QA) | The BHP is to ensure monthly updates and compliance with the Provider Directory, per managed care requirements. The provider directory is to be available to all members. | Both | 100% SMHS and DMC-ODS Program compliance with required Provider Directory monthly updates. | Programs submit updates by the 15th of every month via the 274 UI. MCST will track and monitor the programs' submissions to ensure all programs are accounted for and placed in the online Provider Directory. | The 274 UI sends out emails to the programs on the 1st of every month reminding them that the monthly updates are due by the 15th of the month. A 2nd reminder is sent on the 15th of the month to those who have not submitted provider updates for their programs. The final listings are converted and published/posted on the public facing website on the last business day of the month. Programs that do not submit their monthly updates for 2 consecutive months are subject to a Corrective Action Plan to achieve compliance with the state and federal regulations. For FY 25-26, MCST is to work with HCA IT and IRIS to develop and transition all providers to enter provider directory elements on the 274 User Interface (UI). The 274 UI will be linked to the provider directory website www.bhpproviderdirectory.ochca.com so that any provider updates will be posted within 24 hours of the approved changes. | MCST continues to utilize the existing provider directory workflow as they simultaneously collaborate with HCA IT and EHR SST with developing the new provider directory using the 274 UI and redesigning the provider directory website. Once the 274 UI incorporates the required DHCS fields and the revamped provider directory website it will be tested by the Provider Directory Team. Upon the finalization of the 274 UI and provider directory website redesign, MCST will develop a training guide for providers and administrators. MCST will train all providers on the 274 UI provider directory elements and monthly entry requirements. MCST and HCA IT will create reports to develop an internal workflow to track, reconcile and monitor provider compliance. Anticipated launch and finalizing implementation issues will likely be between November 2025 - February 2026. |  | MCST
Quality Assurance (QA) | To ensure consistent decisions among CRR team staff about the appropriateness of utilization and medical necessity determinations. | Both | CRR team staff conducting documentation reviews will participate in activities to improve inter-rater consistency, at least annually. | All CRR team staff to reach pass/fail agreement 85% of the time. | Clinical staff participating in documentation reviews will attend regularly scheduled meetings which include review and discussion of examples of both acceptable and unacceptable documentation. In addition, at least annually, a formal exercise will be held in which the focus is reviewing of records and developing of concurrence among the review staff regarding the interpretation of standards to be applied during reviews. A write up of this activity will be maintained and included in the annual review of the quality management program. | DMC-ODS reviews were conducted in pairs, then re-reviewed by a third staff to ensure consistency. All reviews were found to be in 100% agreement given this system. AOA Support Team reviews were conducted as a team of 2 or more reviewers. All reviews are re-reviewed by a lead reviewer to ensure consistency. All reviews were found to be in 100% agreement with this system. CYS Support Team reviews were conducted by the lead team consultant. Reliability data was not gathered therefore reliability percentages are not available. |  | CRRT
Quality Assurance (QA) | The BHP is to develop and/or revise and update at least two Practice Guidelines (PG) and trainings annually. | Both | Minimum of four quarterly PG workgroup meetings completed. Minimum of 2 PG completed, published and disseminated. | Practice Guidelines (PG) Workgroup members will develop and implement feedback mechanisms in order to make adjustments to PGs as necessary. The PG Workgroup, PG Development Team, QMS and Program will work together to ensure Practice Guidelines are being implemented. QMS will provide oversight and monitoring to ensure that all PGs are continuously evaluated, monitored and adjusted as necessary. This webpage is found here: https://www.ochealthinfo.com/MHRS/about/QMS/guidelines. | The PG Development and Implementation P&P, was finalized and approved on 11/6/19, which outlines the process for developing and disseminating the practice guidelines to staff. QMS provides direction and guidance regarding BHS practice guidelines during quarterly quality assurance meetings and trains network providers on the approved PG by distributing them for review. Newly developed PGs are announced via email to all BHS Program Managers, Service Chiefs and Program Supervisors, as well as to County contracted Program Managers, with the request that the PGs be reviewed and discussed at staff meetings. PGs are also announced with the webpage link as part of the BHS Director’s Monthly Update to all BHS users. Service Chiefs and Program Managers are also asked to review PGs with newly hired staff during orientation. PGs content are incorporated into the Annual Provider Trainings. Practice Guidelines (Guidelines, Quick Guide, and resources) are posted on the Plan’s Website at http://www.ochealthinfo.com/MHRS/about/QMS/guidelines. | MHP and DMC-ODS Plans developed the following new Practice Guidelines: -BHS Practice Guideline for People with Physical and Cognitive Disabilities (New) 07/2024 -BHS Supervision of Peers Practice Guideline (New) 10/2024 -Quick Guide Prescribing Practices for Psychotropic Medication in Children and Youth (New) 11/2024 -BHS Danger to Others Practice Guideline (New) 12/2024 MHP and DMC-ODS Plans updated the following Practice Guideline: -SUD Perinatal Practice Guideline (Update - Adopted from DHCS) 07/2024 |  | Special Projects
Quality Assurance (QA) | QA/QI meetings be held at least quarterly for SMHS and DMC-ODS QA/QI providers and minutes available. SMHS and DMC-ODS to establish a QI Committee to review the quality of SMHS and SUD treatment services provided to members. | Both | Regularly scheduled QA/QI meetings with the QA and QI County and Contracted providers will be held to review quality improvement data, new requirements, QM processes and quality of care reviews, including documentation issues and feedback from reviews. | At least quarterly, attendance and meeting minutes for SMHS and SUD QI Coordinators and/or CQIC meetings. | BHS shall establish a QI Committee to review the quality of SMHS and DMC-ODS treatment services provided to members. The QI Committee shall recommend policy decisions; review and evaluate the results of QI activities, including performance improvement projects; institute needed QI actions; ensure follow-up of QI processes; and document QI Committee meeting minutes regarding decisions and actions taken. The QI Committee shall review the following data at a minimum on a quarterly basis. | DMC-ODS -- 11 meetings occurred during the FY on a monthly basis except for the month of December. AOA: 6 meetings occurred during the FY CYS: 10 meetings occurred during the FY |  | QI Support
Quality Assurance (QA) | Ensure that all providers identified by DHCS as needing supervision have submitted a Clinical Supervision Form identifying their supervisor. | Both | Documentation of submitted Supervision Reporting Forms to MCST for both plans. Upon review, confirmation by CRR teams that services rendered has been done while under supervision, if applicable. | The MCST will reconcile quarterly using the BHP Provider Directory against the Supervision Reporting Forms to ensure all providers are accounted for. MCST reviews all supervision reporting forms received and completed by the provider to track and log. CRR teams conduct provider reviews of billed services and verify with MCST if all supervision documents are in order for the specific provider to determine whether recoupment is required. | MCST continues to conduct reconciliation of the supervision reporting forms against the BHP Provider Directory. Upon reconciling in its entirety, MCST works to identify providers who have not been receiving supervision. Should this occur MCST will notify the designated CRR team to conduct an individualized review for billed services made by the provider to determine recoupment. MCST will also collaborate with CRR to issue a Notice of Deficiency, if required. MCST also provides several trainings/reminders throughout the year about supervision requirements to County and County-Contracted Clinics at monthly/quarterly meetings. MCST also providers monthly reminders on the SMHS QR Tips and SUD Newsletters when there are trends and updates. | This past year the BHP revised the Clinical Supervision Form to include Clinical Trainee and developed a new form for medical professional, Other Qualified Provider, Certified Peer Specialist and Mental Health Rehabilitation Specialist provider types The BHP tracked, monitored and verified that 100% (2,039 network providers) had submitted a completed Clinical Supervision Form. |  | MCST
Quality Assurance (QA) | 100% of required SMHS and DMC-ODS Health Plans providers will be credentialed in accordance with MCST requirements. | Both | Percentage of eligible providers in each plan that have completed the credentialing process and/or who are in compliance with the necessary steps to complete the process. | Reconciliation of the monthly provider directory against credentialed staff to ensure that all eligible providers reported for each program have been properly credentialed. | MCST credentials all SMHS and DMC-ODS eligible county and contracted providers. 1. BHP provides an updated list under the health plans so that MCST can ensure all programs are accounted for and scheduled to be credentialed. 2. MCST coordinates with each program to compile the required documents for each provider for submission to the credentialing verification organization (Datix). 3. Datix uses the data from these documents to generate a comprehensive report for each provider for the County to review and for final approval for credentialing. | 100% of SUD DMC ODS County Programs were County Credentialed. 100% of AOA MHP County Programs were County Credentialed 100% of CYS MHP County Programs were County Credentialed Of those, there were 2 instances in SUD, 3 instances in SMHS where providers rendered services prior to receiving a credentialing approval notice, which was addressed with the organizational provider and practitioner to establish corrective actions and repayments as needed. All were subsequently credentialed and retrained. |  | MCST
Quality Assurance (QA) | Network providers will receive training on the requirements and elements of the SMHS and the DMC-ODS annually. Training will be completed for all County and Contracted clinical staff and appropriate administrators to ensure all network providers are aware of the SMHS and DMC-ODS requirements at least annually. | Both | 100% compliance with completion of the mandatory Annual Provider Training (APT) for all County and Contracted clinical staff claiming to Medi-Cal for SMHS and for County and Contracted clinical staff claiming to DMC-ODS that addresses the various requirements of the plans, including appropriate documentation of services. | Annual Training released within the Fiscal Year with 100% completion, as measured by attestation from the Service Chief or Program Director. Evidence of completion of the APT is required prior to any provider being credentialed by the County and prior to being granted access into the county's IRIS - EHR for billing and documentation. | HCA shall ensure that all subcontractors (providers) receive training on the SMHS and DMC-ODS requirements, at least annually. HCA shall report compliance with this requirement to DHCS annually as part of the DHCS County Monitoring process. Service providers are required to take an annual training that includes multiple topics. One of these topics is appropriate documentation of services under the SMHS and DMC-ODS. Training includes examples of acceptable and unacceptable documentation; issues that have been identified by audit/review staff or others as needing improvement during the prior year; reminders of the ways in which staff may obtain guidance for their documentation questions; and other general documentation issues. There are several versions of this training, so that each provider may take the one that most closely matches his/her work assignment. It is a contract requirement for both SMHS and DMC-ODS providers that their staff complete this training at least annually. | 2025 Annual Provider training was completed by 100% of county and contract clinical staff and appropriate administrators. |  | Technical Assistance & Training Support (TATS)
Quality Assurance (QA) | To provide support to providers to ensure compliant documentation practices at all times documentations manual for the SMHS and DMC-ODS services will be maintained by QMS. The documentation manuals will address specific documentation requirements, including content as well as timelines. | Both | The SMHS and DMC-ODS documentation manuals will be updated as needed to reflect changes to documentation and documentation requirements. Update to be completed and circulated and key elements added to the Documentation Manual. CRR teams to review at QI Coordinators Meeting. Information to be distributed in the monthly SMHS QRTips and SUD newsletter. | Dated versions on the manual. Manual distribution and posting on website upon revision. | BHS has a wide array of programs and some programs may have specific variances from the standard requirements. The documentation manuals will be updated as needed. The various requirements and changes of California Advancing and Innovating Med-Cal (CalAIM) were reflected on revisions to the documentation manual beginning year, FY22/23. | DMC-ODS: An updated DMC-ODS Documentation Manual was released and posted on the provider webpage. Updates to documentation requirements were circulated through the provider newsletter as well as at monthly QIC meetings. Updates to the CPT guide based on payment reform and MAT Documentation Manual were released. MHP: Updates to documentation requirements were circulated through the provider newsletter as well as at monthly QIC meetings. Updates to the CPT codes and Payment Reform information were made via provider specific Coding Quick Guides shared with all providers and posted on agency internet. |  | TATS
Quality Assurance (QA) | Ensure that evidence of documentation exists in the member record to show that consent for services via telehealth was obtained when services are provided through telehealth. | Both | Member records shall evidence that consent for services via telehealth was obtained from the member and documented in the chart, with 100% compliance for this requirement evidenced in records reviewed. | Through records/documentation reviews, the CRR teams will determine if there is evidence of consent for telehealth services on the records reviewed. This information is captured through the clinical record monitoring tool, which prompts for recording yes/no if consent for telehealth is found on each record. | State law requires the health care provider initiating the use of telehealth to inform the member, obtain consent, and maintain appropriate documentation. Providers at both the originating and distant site should maintain documentation in the member's medical record in the event health records are not shared. If a health care provider or health care group/organization has a general consent protocol that specifically references use of telehealth as a modality, then this would satisfy the consent requirement. | AOA & CYS: Clinical records reviews confirm that all telehealth services are provided with a signed telehealth consent. Quality of care comments are provided whenever a consent is missing and providers are asked to obtain consent immediately. DMC-ODS: FY 24-25 Clinical Records Review evidence results are that consent was obtained for services via telehealth (when services were provided through Telehealth) in 96.45% of the charts reviewed. |  | DAE / CRRT
Quality Assurance (QA) | Ensure that evidence of documentation exists in the member record to show that providers confirmed that a member is physically located in California when services are provided through telehealth. | Both | Member records shall evidence that the member's location in California at the time of service was confirmed, with 100% compliance for this requirement evidenced in records reviewed. | Through records/documentation reviews, the CRR teams will determine if there is evidence of consent for telehealth services on the records reviewed. This information is captured through the clinical record monitoring tool, which prompts for recording yes/no if consent for telehealth is found on each record. | Members must be eligible for Medi-Cal in order to receive Medi-Cal covered services through telehealth. | AOA & CYS: Per clinical records review, MHP providers document the member’s location and address in each telehealth or telephonic progress note which ensures that the member is located in California during the time of service. DMC-ODS FY 24-25 Clinical Records Review: Documentation that the provider confirmed that the member is physically located in California was found in 85.98% of the charts reviewed. |  | DAE / CRRT
Quality Assurance (QA) | All eligible SMHS will complete required DHCS Provider Enrollment on an ongoing basis. | SMHS | 100% of county operated eligible Licensed Practitioner of the Healing Arts (LPHA) staff will be enrolled in PAVE. | Fulfillment of PAVE enrollment will be embedded into BHS' existing onboarding process (i.e. PAN form) ensuring that only enrolled rendering providers are able to bill for services. | DHCS requires that all eligible LPHA be enrolled in PAVE. MCST confirms that the rendering provider’s application was approved by DHCS PED via viewing and downloading the data found at DHCS’ Open Data Portal (https://data.chhs.ca.gov/dataset/profile-of-enrolled-medi-cal-fee-for-service-ffs-providers/resource/a9967f81-aaa4-475e-8cd8-459dcc1be2df?inner_span=True). Per DHCS PED, approval of an ORP application may take up to 180 days. MCST tracks and monitors SMHS providers regularly by reconciling the providers against the Provider Directory to ensure all required providers for county and county-contracted are PAVE enrolled. | # of CYS Enrolled PAVE Providers: 448 # of AOA Enrolled PAVE Providers: 369 MCST conducts regular reconciliation against the provider directory to account for all SMHS PAVE Enrollees and ensures they are enrolled successfully at 100% compliance. |  | MCST
Quality Assurance (QA) | Obtain compliance with California Outcome Measurement Systems (CalOMS) reporting requirements, including timely submission of required records and reducing data errors. The DMC-ODS Plan will have a 95% compliance rate. | DMC-ODS | CalOMS data will be submitted on time and without error to DHCS and compliance rate will be tracked. | The CalOMS Open Admission Report will be run out of the DHCS BHIS platform to ensure completeness and timely submission of records. | In the upcoming FY, the plan will continue to work with providers to reduce these errors and to bring all submissions up to date. The CalOMS requirement will continue to be addressed in the monthly QI coordinators meetings and plans for correction will continue to be developed to ensure that the system’s overall compliance rate remains at 95% or above. | The plan continued to maintain full compliance with CalOMS submission requirements. This goal will remain active to ensure ongoing focus on this item. |  | Healthcare Effectiveness Data and Information Set (HEDIS) & Performance Outcome Measures (POM)
Quality Assurance (QA) | Complete annual updates of the Cultural Competence (CC) Plan to ensure culturally appropriate services to members. | Both | Completion and submission of the CC Plan. | The CC Plan will continue to utilize SAMHSA's Recovery Model and BHS Equity Social and Mental Health (ESM) will complete the plan in collaboration with the community, peers, providers and additional key stakeholders. | Based upon these goals and guiding principles, we offer our CC Plan Update. The plan remains grounded in the philosophy of SAMHSA’s Recovery Model and seeks to reach out to the community in close collaboration, to assist in building a more resilient and hopeful Orange County in the coming years. BHS continues to believe that individuals with mental illnesses or addictions can recover and be members of a thriving community. Therefore, it is our hope that this CC Plan update will help move BHS further along the journey toward increased mental health equity for those whom we serve. | The cultural competence plan was submitted as required. |  | Office of Equity
Quality Assurance (QA) | Increase the number of members who transition from Residential treatment services into Outpatient services within 7 days of Residential discharge to 30%. | DMC-ODS | Percentage of members who attend an outpatient appointment with a DMC-ODS Outpatient provider within 7 days or discharge from Residential treatment. | Charge data will be utilized to identified unique members who are discharged from a network residential treatment program and then admitted into an outpatient programs within 7 days of the Residential discharge. | The rates of residential transition into outpatient treatment have been lower than expected. This metric has been tracked since 2018, implementing multiple QA activities, including adding it to providers' monthly contract monitoring meeting agendas, offering the aid of peers at specific residential programs to assist with transitions, discussing challenges and opportunities in the SUD QI coordinators meetings and ultimately adding it to contracted provider's contracts as performance outcomes. These multiple activities have resulted in gradual increases in transition rates over time. | In FY 24/25, 26.9% of residential discharges linked to a lower level of care (outpatient services) within 7 days of discharge, exceeding the goal of 20% and representing an increase from the FY 23/24 linkage rate of 23.6%. Additionally, 49.8% of members linked to a lower level of care within 30 days of residential discharge, an increase from the previous FY. |  | DAE / QI Support
Quality Assurance (QA) | Achieve a 30-day follow-up rate after an emergency department visit that meets or exceeds the NCQA minimum performance level (MPL) for the Follow-Up After Emergency Department Visit for Mental Illness (FUM) HEDIS measure. | SMHS | 1. FUM rate that meets or exceeds the MPL for MY 2024 or demonstrates a 5% point increase over the MPL for MY 2023. 2. Fully automated 837 file exchange with MCPs. 3. Integrated MMEF eligibility file into measure logic. 4. Implemented follow-up process for patients upon ED discharge. 5. Migrate measure logic away from Plan Data Feed and towards 837 files. | 1. Develop 837 file transfer protocol with MCPs (Kaiser Permanente/CalOptima). 2. Prepare, optimize, and transform 837 files for FUM rate calculation. 3. Identify Hospital partner(s) to collaborate and implement follow-up process for patients upon ED discharge. | Ensure patients receiving emergency care for mental health crises have timely follow-up within 30 days to improve outcomes and reduce readmissions. Establish an automated data exchange framework with Kaiser Permanente and CalOptima using 837 files to track ED discharges and outpatient follow-up care. Collaborate with hospital partner to design and implement a follow-up process that identifies patients discharged from ED and ensures they complete a follow-up visit within 30 days of discharge. | FUM Measurement Year 2025: 30-day follow-up rate of 62.6% 7-day follow-up rate of 41.1% *Note rates are based on CY utilizing the Plan Data Feed files and 2025 Minimum Performance Level has not yet been posted. |  | DAE
Quality Assurance (QA) | Achieve a 30-day follow-up rate after an emergency department visit that meets or exceeds the NCQA minimum performance level (MPL) for the Follow-Up After Emergency Department Visit for Alcohol or Other Substance Use (FUA) HEDIS measure. | DMC-ODS | 1. FUA rate that meets or exceeds the MPL for MY 2024 or demonstrates a 5% point increase over the MPL for MY 2023. 2. Fully automated 837 file exchange with MCPs. 3. Integrated MMEF eligibility file into measure logic. 4. Implemented follow-up process for patients upon ED discharge. 5. Clearly defined category of Mental Health Provider. 6. Migrate measure logic away from Plan Data Feed and towards 837 files. | 1. Develop 837 file transfer protocol with MCPs (Kaiser Permanente, CalOptima). 2. Prepare, optimize, and transform 837 files for FUA rate calculation. 3. Identify Hospital partner(s) to collaborate and implement follow-up process for patients upon ED discharge. | Ensure patients receiving emergency care for substance use have timely follow-up within 30 days to improve outcomes and reduce readmissions. Establish an automated data exchange framework with Kaiser Permanente and CalOptima using 837 files to track ED discharges and outpatient follow-up care. Collaborate with hospital partner to design and implement a follow-up process that identifies patients discharged from ED and ensures they complete a follow-up visit within 30 days of discharge. | FUA Measurement Year 2025: 30-day follow-up rate of 50.5% 7-day follow-up rate of 32.2% *Note rates are based on CY utilizing the Plan Data Feed files and 2025 Minimum Performance Level has not yet been posted. |  | DAE
Quality Assurance (QA) | Achieve a 30-day follow-up rate after hospitalization that meets or exceeds the NCQA minimum performance level for the Follow-Up After Hospitalization for Mental Illness (FUH) HEDIS measure. | SMHS | 1. Fully automated 837 file exchange with MCPs. 2. Integrated MMEF eligibility file into measure logic. 3. NCQA approved definition of Mental Health Provider. 4. Migrate measure logic away from Plan Data Feed and towards 837 files. | 1. Develop 837 file transfer protocol with MCPs (Kaiser Permanente, CalOptima). 2. Prepare, optimize, and transform 837 files for FUH rate calculation. 3. Develop Measure logic and calculation of rates. | The existing DHCS Plan Data Feed (PDF) presents two major challenges for OCHCA’s ability to serve our Medi-Cal population effectively. First, updates are delayed by thirty days or more, creating a lag in critical data availability. Second, the PDF only tracks Medi-Cal patients seen within the OCHCA ecosystem, omitting those served by other providers in the county. These limitations hinder timely interventions and prevent a complete understanding of our Medi-Cal population’s needs. The transition to 837 files represents a powerful solution to these challenges while delivering additional strategic benefits. As standardized files conforming to ANSI X12 standards, they are recognized by NCQA as an administrative data source. This classification offers both operational and compliance advantages, significantly streamlining our HEDIS reporting process while maintaining data integrity across different MCPs (including Kaiser Permanente and CalOptima). The practical impact of this transition will be transformative. Daily file transfers will replace the current month-long delays, providing near real-time data to support timely interventions and care coordination. Critically, 837 files will expand our visibility to include all Medi-Cal patients served anywhere within Orange County, regardless of their provider. This represents a quantum leap in our capacity to understand and serve our entire Medi-Cal population. | FUH Measurement Year 2025: 30-day follow-up rate of 61.9% 7-day follow-up rate of 43.4% *Note rates are based on CY utilizing the Plan Data Feed files and 2025 Minimum Performance Level has not yet been posted. |  | DAE
Quality Assurance (QA) | Achieve Antidepressant Medication Management (AMM) rates that meet or exceed the NCQA minimum performance levels : 1) AMM Effective Acute Phase Treatment and 2) AMM Effective Continuation Phase Treatment | SMHS | 1. Fully automated 837 file exchange with MCPs. 2. Integrated MMEF eligibility file into measure logic. 3. Migrate measure logic away from Plan Data Feed and towards 837 files. | 1. Develop 837 file transfer protocol with MCPs (Kaiser Permanente, CalOptima). 2. Prepare, optimize, and transform 837 files for AMM rate calculation. 3. Develop Measure logic and calculation of rates. | The existing DHCS Plan Data Feed (PDF) presents two major challenges for OCHCA’s ability to serve our Medi-Cal population effectively. First, updates are delayed by thirty days or more, creating a lag in critical data availability. Second, the PDF only tracks Medi-Cal patients seen within the OCHCA ecosystem, omitting those served by other providers in the county. These limitations hinder timely interventions and prevent a complete understanding of our Medi-Cal population’s needs. The transition to 837 files represents a powerful solution to these challenges while delivering additional strategic benefits. As standardized files conforming to ANSI X12 standards, they are recognized by NCQA as an administrative data source. This classification offers both operational and compliance advantages, significantly streamlining our HEDIS reporting process while maintaining data integrity across different MCPs (including Kaiser Permanente and CalOptima). The practical impact of this transition will be transformative. Daily file transfers will replace the current month-long delays, providing near real-time data to support timely interventions and care coordination. Critically, 837 files will expand our visibility to include all Medi-Cal patients served anywhere within Orange County, regardless of their provider. This represents a quantum leap in our capacity to understand and serve our entire Medi-Cal population. | The AMM measure is no longer included in the BHAS measure set for Measurement Year (MY) 2025 |  | DAE
Quality Assurance (QA) | Achieve medication adherence rate that meets or exceeds the NCQA minimum performance level for the Adherence to Antipsychotic Medications for Individuals with Schizophrenia (SAA) measure. | SMHS | 1. Fully automated 837 file exchange with MCPs. 2. Integrated MMEF eligibility file into measure logic. 3. Migrate measure logic away from Plan Data Feed and towards 837 files. | 1. Develop 837 file transfer protocol with MCPs (Kaiser Permanente, CalOptima). 2. Prepare, optimize, and transform 837 files for SAA rate calculation. 3. Develop Measure logic and calculation of rates. | The existing DHCS Plan Data Feed (PDF) presents two major challenges for OCHCA’s ability to serve our Medi-Cal population effectively. First, updates are delayed by thirty days or more, creating a lag in critical data availability. Second, the PDF only tracks Medi-Cal patients seen within the OCHCA ecosystem, omitting those served by other providers in the county. These limitations hinder timely interventions and prevent a complete understanding of our Medi-Cal population’s needs. The transition to 837 files represents a powerful solution to these challenges while delivering additional strategic benefits. As standardized files conforming to ANSI X12 standards, they are recognized by NCQA as an administrative data source. This classification offers both operational and compliance advantages, significantly streamlining our HEDIS reporting process while maintaining data integrity across different MCPs (including Kaiser Permanente and CalOptima). The practical impact of this transition will be transformative. Daily file transfers will replace the current month-long delays, providing near real-time data to support timely interventions and care coordination. Critically, 837 files will expand our visibility to include all Medi-Cal patients served anywhere within Orange County, regardless of their provider. This represents a quantum leap in our capacity to understand and serve our entire Medi-Cal population. | SAA Measurement Year 2025: Rate of 69.8% *Note rates are based on CY utilizing the Plan Data Feed files and 2025 Minimum Performance Level has not yet been posted. |  | DAE
Quality Assurance (QA) | Ensure that youth prescribed an anti-psychotic medication first receive psychosocial care at a rate that meets or exceeds the NCQA minimum performance level for the First-Line Psychosocial Care for Children and Adolescents on Antipsychotics (APP) measure. | SMHS | 1. Fully automated 837 file exchange with MCPs. 2. Integrated MMEF eligibility file into measure logic. 3. Migrate measure logic away from Plan Data Feed and towards 837 files. | 1. Develop 837 file transfer protocol with MCPs (Kaiser Permanente, CalOptima). 2. Prepare, optimize, and transform 837 files for APP rate calculation. 3. Develop Measure logic and calculation of rates. | The existing DHCS Plan Data Feed (PDF) presents two major challenges for OCHCA’s ability to serve our Medi-Cal population effectively. First, updates are delayed by thirty days or more, creating a lag in critical data availability. Second, the PDF only tracks Medi-Cal patients seen within the OCHCA ecosystem, omitting those served by other providers in the county. These limitations hinder timely interventions and prevent a complete understanding of our Medi-Cal population’s needs. The transition to 837 files represents a powerful solution to these challenges while delivering additional strategic benefits. As standardized files conforming to ANSI X12 standards, they are recognized by NCQA as an administrative data source. This classification offers both operational and compliance advantages, significantly streamlining our HEDIS reporting process while maintaining data integrity across different MCPs (including Kaiser Permanente and CalOptima). The practical impact of this transition will be transformative. Daily file transfers will replace the current month-long delays, providing near real-time data to support timely interventions and care coordination. Critically, 837 files will expand our visibility to include all Medi-Cal patients served anywhere within Orange County, regardless of their provider. This represents a quantum leap in our capacity to understand and serve our entire Medi-Cal population. | APP Measurement Year 2025: Rate of 77.4% *Note rates are based on CY utilizing the Plan Data Feed files and 2025 Minimum Performance Level has not yet been posted. |  | DAE
Quality Assurance (QA) | Achieve a pharmacotherapy treatment rate that meets or exceeds the NCQA minimum performance level for the Pharmacotherapy for Opioid Use Disorder (POD) measure. | DMC-ODS | 1. Fully automated 837 file exchange with MCPs. 2. Integrated MMEF eligibility file into measure logic. 3. Migrate measure logic away from Plan Data Feed and towards 837 files. | 1. Develop 837 file transfer protocol with MCPs (Kaiser Permanente, CalOptima). 2. Prepare, optimize, and transform 837 files for POD rate calculation. 3. Develop Measure logic and calculation of rates. | The existing DHCS Plan Data Feed (PDF) presents two major challenges for OCHCA’s ability to serve our Medi-Cal population effectively. First, updates are delayed by thirty days or more, creating a lag in critical data availability. Second, the PDF only tracks Medi-Cal patients seen within the OCHCA ecosystem, omitting those served by other providers in the county. These limitations hinder timely interventions and prevent a complete understanding of our Medi-Cal population’s needs. The transition to 837 files represents a powerful solution to these challenges while delivering additional strategic benefits. As standardized files conforming to ANSI X12 standards, they are recognized by NCQA as an administrative data source. This classification offers both operational and compliance advantages, significantly streamlining our HEDIS reporting process while maintaining data integrity across different MCPs (including Kaiser Permanente and CalOptima). The practical impact of this transition will be transformative. Daily file transfers will replace the current month-long delays, providing near real-time data to support timely interventions and care coordination. Critically, 837 files will expand our visibility to include all Medi-Cal patients served anywhere within Orange County, regardless of their provider. This represents a quantum leap in our capacity to understand and serve our entire Medi-Cal population. | The DAE team is actively working on this item; it is currently in progress |  | DAE
Quality Assurance (QA) | Achieve treatment rates that meet or exceed the NCQA minimum performance levels for the Initiation and Engagement of Substance Use Disorder Treatment (IET) measures. Two rates are reported: 1) Initiation of SUD Treatment and 2) Engagement of SUD Treatment. | DMC-ODS | 1. Fully automated 837 file exchange with MCPs. 2. Integrated MMEF eligibility file into measure logic. 3. Migrate measure logic away from Plan Data Feed and towards 837 files. | 1. Develop 837 file transfer protocol with MCPs (Kaiser Permanente, CalOptima). 2. Prepare, optimize, and transform 837 files for IET rate calculation. 3. Develop Measure logic and calculation of rates. | The existing DHCS Plan Data Feed (PDF) presents two major challenges for OCHCA’s ability to serve our Medi-Cal population effectively. First, updates are delayed by thirty days or more, creating a lag in critical data availability. Second, the PDF only tracks Medi-Cal patients seen within the OCHCA ecosystem, omitting those served by other providers in the county. These limitations hinder timely interventions and prevent a complete understanding of our Medi-Cal population’s needs. The transition to 837 files represents a powerful solution to these challenges while delivering additional strategic benefits. As standardized files conforming to ANSI X12 standards, they are recognized by NCQA as an administrative data source. This classification offers both operational and compliance advantages, significantly streamlining our HEDIS reporting process while maintaining data integrity across different MCPs (including Kaiser Permanente and CalOptima). The practical impact of this transition will be transformative. Daily file transfers will replace the current month-long delays, providing near real-time data to support timely interventions and care coordination. Critically, 837 files will expand our visibility to include all Medi-Cal patients served anywhere within Orange County, regardless of their provider. This represents a quantum leap in our capacity to understand and serve our entire Medi-Cal population. | The DAE team is actively working on this item; it is currently in progress |  | DAE
Quality Assurance (QA) | Achieve a medication treatment rate that meets or exceeds the NCQA minimum performance level for the Use of Pharmacotherapy for Opioid Use Disorder (OUD) measure. | DMC-ODS | 1. Fully automated 837 file exchange with MCPs. 2. Integrated MMEF eligibility file into measure logic. 3. Migrate measure logic away from Plan Data Feed and towards 837 files. | 1. Develop 837 file transfer protocol with MCPs (Kaiser Permanente, CalOptima). 2. Prepare, optimize, and transform 837 files for OUD rate calculation. 3. Develop Measure logic and calculation of rates. | The existing DHCS Plan Data Feed (PDF) presents two major challenges for OCHCA’s ability to serve our Medi-Cal population effectively. First, updates are delayed by thirty days or more, creating a lag in critical data availability. Second, the PDF only tracks Medi-Cal patients seen within the OCHCA ecosystem, omitting those served by other providers in the county. These limitations hinder timely interventions and prevent a complete understanding of our Medi-Cal population’s needs. The transition to 837 files represents a powerful solution to these challenges while delivering additional strategic benefits. As standardized files conforming to ANSI X12 standards, they are recognized by NCQA as an administrative data source. This classification offers both operational and compliance advantages, significantly streamlining our HEDIS reporting process while maintaining data integrity across different MCPs (including Kaiser Permanente and CalOptima). The practical impact of this transition will be transformative. Daily file transfers will replace the current month-long delays, providing near real-time data to support timely interventions and care coordination. Critically, 837 files will expand our visibility to include all Medi-Cal patients served anywhere within Orange County, regardless of their provider. This represents a quantum leap in our capacity to understand and serve our entire Medi-Cal population. | OUD Measurement Year 2025: Rate 2: BUPRENORPHINE of 29.5% Rate 3: ORAL_NALTREXONE of 4.3% Rate 4: LONG_ACTING_INJECTABLE_NALTREXONE of 1.3% Rate 5: METHADONE of 45.4% Rate 1: TOTAL of 73.0% *Note rates are based on CY utilizing the Plan Data Feed files and 2025 Minimum Performance Level has not yet been posted. |  | DAE
Quality Assurance (QA) | Implementation of new systems and practices to support Payment Reform under CalAIM. | Both | Publishing training guides and CPT code manuals to assist network providers in implementing new documentation standards. Updating County information systems and EHR to enable implementation and transmission of new CPT codes and publishing Intergovernmental Transfers (IGT) P&P. | QMS staff will develop new CPT guides and training manuals to ensure all network providers are aware of this policy. This metric will be measured by the presence of IGT P&P drafts and applicable notices/memos to providers. | DHCS issued guidance and readiness checklist resources to enable counties to implement Payment Reform. OCHCA will avail itself of policy guidance, technical assistance, and incentive funding to ensure appropriate information and financial resources to implement Payment Reform This initiative will require multiple OCHCA service areas, including Information Technology, Program Support/Fiscal, Contracts/Procurement, QMS billing and EHR and impacted network providers. QMS staff will work with various other area leads and subject matter experts (SME) to implement each stage of the change from identifying relevant CPT codes to be used and building them in the EHR and billing systems to creating training and resource guides to communicating with impacted providers frequently through various means, including QMS QI coordinators meetings and distribution lists; communication from the BHS director and Contracts/Procurement. | Progress was made during this fiscal year and the goal was partially met. EHR system updates were made; however, given the complexity of Payment Reform implementation, all requirements were not completed by the end of the year. Provider contracts and reimbursement methodologies were updated to begin, effective July 2025. Other system changes remain needed. This goal will be carried forward to FY25-26 |  | DAE / TATS / Program Support (PS) / Information Technology (IT) / Contracts
Quality Assurance (QA) | Development and focus on improving data sharing and information management capabilities. | Both | Establishing processes for effective and efficient data exchange with the MCP and treating providers. | Establishment of agreement with QHIO. Participation in DCHS PH Medi-Cal Connect Advisory group activities. | As of the beginning of the FY, BHS does not participate in a Health Information Exchage (HIE) and relies primarily on internal charge data for tracking and performance measurement. This year, the focus will be on securing participation in an HIE/QHIO and/or another secure data exchange process to improve utilization management and coordination of care. | This goal was partially met. Orange BHP released a solicitation for HIE/QHIO and expects to implement an agreement by the next FY. Orange BHP is working on establishing data exchange processes and workflows with CalOptima Health to improve performance outcomes on the BHAS. Orange BHP concluded participation in Medi-Cal Connect advisory group. |  | DAE
Utilization Management (UM) | All TAR data is to be reported and reviewed by QMS quarterly to identify potential areas of attention. | SMHS | 1) The number of TAR denials appealed by providers, 2) The results of TAR 1st level appeals, 3) The results of TAR 2nd level appeals. The report will be reviewed at least annually by the CQIC. | Review of quarterly submitted TAR data. Inpatient acute psychiatric hospital providers submit TARs for approval to the SMHS to request reimbursement for services provided to Medi-Cal members. SMHS monitors the results of the TAR approval process as well as provider appeals of TAR denials. IDSS team will submit to DAE quarterly a summary report of 1) The number of TAR denials appealed by providers, 2) The results of TAR 1st level appeals, 3) The results of TAR 2nd level appeals. The report will be reviewed at least annually by the CQIC. | IDSS team is responsible for the review and approval of all TARs submitted. TAR data is to be tracked and quarterly reporting to DAE is required. | Total number of appeals-44 1st Level Appeal Total-41 Total overturned-24 Total Upheld-17 2nd Level Appeals Total-3 All 3 were upheld |  | IDSS
Utilization Management (UM) | Compliance rate at least 99%. for evidence of stamping with completion date that are consistent with the database used for reporting timeliness of TAR processing. | SMHS | Hospital TARs are to be processed within 14 calendar days. The report will be reviewed at least annually by the CQIC. | An annual report on timeliness of TAR processing will be produced and reviewed in the CQIC. QMS to review a small sample to ensure compliance. A step will be added in which QMS reviews a small sampling of the TARs to ensure that the date stamp and completion date are consistent with the data base from which the annual report is prepared. | IDSS team is responsible for the review and approval of all TARs submitted. TAR data is to be tracked and quarterly reporting to DAE is required. | A total of 8,584 TARs were signed. 68.6% were signed within 14 days and 31.4% were signed after 14 days |  | IDSS
Utilization Management (UM) | Review inpatient data for potential patterns and trends in hospitalization, conduct a root cause analysis on any identified patterns, and develop QI strategies, as needed, to address potential root causes underlying inpatient hospitalization of members. | SMHS | TAR data evaluation to identify possible trends and to identify baselines for this measure. | Examine TAR data and concurrent review processes to determine if patterns exist in hospitalizations. Based on analytics, establish goals that can be tracked and acted upon. | This measure is intended to evaluate the hospitalization trends in the county in a more system fashion to identify trends and care coordination needs. This data will assist the BHP in developing strategies to address preventable hospitalizations and timely follow up when admissions occur. | This goal was not met for FY24-25 No UM activities were identified as our data was not available in real time to identify these episodes as they occurred. In the past year, a Utilization Management and Complex Care Coordination (UMCC) team was established to enable more timely UR activities. A DAE function area has also increased data analytics capabilities which are expected to be able to support automation of data to identify the target population for this metric. Baselines will be established in FY25-26 following the implementation of automation of TAR processes, using the electronic data transmission solution through Chorus . |  | IDSS
Utilization Management (UM) | Increase effective withdrawal from substances and successful transition to lower level of care by providing additional utilization management to identify additional services or resources needed to individuals who present for a second admission to Withdrawal Management (WM) within 90 days. 50% of admissions will be reviewed. | DMC-ODS | Cases that present for a second admission for withdrawal management services without any other services will be identified and submitted for utilization review to provide treatment engagement recommendations. Percentage of cases reviewed. Percentage of members who accept additional services as a result of the UR process. | 50% of WM admission that present for a second admission without other services in between the two admission will be reviewed by the Utilization Management and Complex Care Coordination (UMCC) team through a utilization review process. The review process will be documented and recommendations provided. | DMC-ODS members who present for a second withdrawal management admission within the year may be at higher risk for leaving treatment prematurely or unsuccessfully. By providing additional review strategies, it is expected that transition to the next appropriate level of care will be more likely. Members who do not successfully link to a longer term appropriate level of care are at higher risk of relapse and needing additional withdrawal management services. Supporting members upon the second admission will provide a mechanisms for increasing treatment success at this level of care and transition to the next level of care to reduce utilization of withdrawal management LOC appropriately. | This goal was not met for FY24-25 No UR activities were offered to these clients as our data was not available in real time to identify these episodes as they occurred. In the past year, a UMCCC team was established to enable more timely UR activities. A DAE function area has also increased data analytics capabilities which are expected to be able to support automation of data to identify the target population for this metric. |  | UMCCC / DAE
Utilization Management (UM) | Increase residential treatment stay success and transition to lower level of care by providing additional utilization management to individuals who present for a second admission to Residential treatment within 90 days to identify additional services or resources needed. 50% of admissions will be reviewed. | DMC-ODS | Cases that present with a second request for Residential treatment authorization will be identified and submitted for utilization review to provide treatment retention recommendations. Percentage of cases reviewed. Percentage of members who accept additional services as a result of the UR process. | 50% of Residential admissions that present for a second admission without other services in between the two admission will be reviewed by the UMCCC team through a utilization review process. The review process will be documented and recommendations provided. | DMC-ODS members who present for a second residential stay within the year may be at higher risk for leaving treatment prematurely or unsuccessfully. By providing additional review strategies, it is expected that transition to the next appropriate level of care will be more likely. Members are entitled to two residential stays per year. Supporting members upon the second admission will provide a mechanisms for increasing treatment success at this level of care and transition to the next level of care to reduce utilization of residential LOC appropriately. | This goal was not met for FY24-25 No UR activities were offered to these clients as our data was not available in real time to identify these episodes as they occurred. In the past year, a UMCCC team was established to enable more timely UR activities. A DAE function area has also increased data analytics capabilities which are expected to be able to support automation of data to identify the target population for this metric. |  | UMCCC / DAE
Utilization Management (UM) | All requests for authorization of residential services will be tracked to monitor network capacity. | DMC-ODS | Number of authorization requests received by the Assessment/Authorization for Residential Treatment (ART) team. Number of treatment denials. Number of treatment modification decisions. Number of appealed decisions. Number of State Fair Hearings. Outcomes for appeals and State Fair Hearings. | ART will submit to MCST a monthly summary report of activity to create a residential services authorization report. The report will be reviewed at least annually and the information will be reviewed reported periodically at the CQIC and/or SUD QI Coordinators meeting. | The ART team receives requests from providers for authorization of residential services for substance use disorders. BHS monitors the results of the authorization approval process as well as provider appeals of denied or reduced authorizations. The ART team will submit to MCST a monthly summary report of activity to create a residential services authorization report. The report will provide the following information, with the information for authorization requests submitted by providers. 1) The number of authorization requests 2) The number of authorization denials 3) the number of authorization reductions/modifications. The QMS MCST will review 1) The number of authorization denials appealed by providers 2) The results of the appeals of the denials 3) The number of authorization reductions appealed by providers 4) The results of the appeals of the reductions 5) The number of State Fair Hearings 6) The outcome of State Fair Hearings. The report will be reviewed at least quarterly with the CQIC. | FY 24/25 ART had 2,128 requests for residential services (July 1, 2024 - June 30, 2025) ART issued 15 NOABD Denials and 0 NOABD Modifications. |  | QI Support
Utilization Management (UM) | Render residential treatment authorization decisions within 24 hours of request 100% of the time. | DMC-ODS | Percentage of residential authorization decisions that are delayed beyond 24 hours, resulting in "Authorization Delay" NOABD issued. | Compliance rate at 100%. SUD Residential Treatment Authorization Requests are to be processed within 24 hours of receipt. An annual report on timeliness of processing will be submitted by the Residential Treatment Authorization team to MCST and the report will be reviewed in the Divisional or CQIC meeting. | Prior authorization determinations for residential treatment within 24 hours of the service authorization request. Member is to receive notice of any decision to deny a service authorization request or to authorize a service in an amount, duration, or scope that is less than requested. | 100% Compliance as ART/Residential Treatment issued 0 NOABD for Delayed Authorization for FY 24-25. |  | MCST
Utilization Management (UM) | Monitor Residential authorization outcomes to ensure appropriate utilization and clinical decisions. | DMC-ODS | Number of Residential authorizations resulting in appeals and reductions of service. 1) The number of authorization denials appealed by providers 2) The results of the appeals of the denials 3) The number of authorization reductions appealed by providers 4) The results of the appeals of the reductions. | Percentage of residential authorization : • Denials • Denial Appeals • Reductions • Reductions appeals • Number and outcome of State Fair Hearings Relative to total authorization requests. The results will be reviewed at least quarterly in the Divisional or CQIC meeting. | The ART team receives requests from providers for authorization of residential services for substance use disorders. BHS monitors the results of the authorization approval process as well as provider appeals of denied or reduced authorizations. The ART teams submits to MCST a monthly summary report of activity to create a residential services authorization report. The report will provide the following information, with the information for authorization requests submitted by providers. 1) The number of authorization requests 2) The number of authorization denials 3) the number of authorization reductions/modifications. The MCST will review 1) The number of authorization denials appealed by providers 2) The results of the appeals of the denials 3) The number of authorization reductions appealed by providers 4) The results of the appeals of the reductions. 5) The number of State Fair Hearings 6) The outcome of State Fair Hearings. | FY 24/25 ART had 2,128 requests for residential services (July 1, 2024 - June 30, 2025)ART (AOA Westminster SUD / The ART Team) issued: 15 NOABD Denials 197 NOABD Terminations 0 NOABD Modifications 0 NOABD Timely Access FY24/25 Termination NOABDs issued by only AOA Westminster SUD / The ART Team: 197 |  | DAE / MCST
Utilization Management (UM) | Conduct monitoring of services clinical records reviews to evaluate utilization and documentation compliance through clinical records review. | Both | Documentation monitoring audits for the SMHS and DMC-ODS providers will be conducted at least annually to provide feedback to providers on documentation as well as quality of care issues. | At least one clinical monitoring review for each network provider will occur during the Fiscal Year. The review will be conducted by each CRR team for their respective programs. | County and contracted service providers will be subject to periodic internal sampling reviews at least once per year. For County clinics, services will be reviewed at least annually. Decisions on sampling may be modified for the SMHS or DMC-ODS Plans depending of system needs. (Example; use of criteria such as random selection of claims or the selection of claims based on the following criteria: high cost paid claims (of 1,000 dollars or more), claims that show higher than usual times claimed and paid claims which appear to be duplicates). At least 40 paid claims will be selected and reviewed by the CRR teams to ensure appropriate billing and to ensure the documentation meets County, State and Federal documentation standards. Feedback will be provided to the Supervisor and Program Manager of the unit reviewed and follow up will conducted to ensure that any ineligible services have been appropriately repaid, as necessary. The number of claims reviewed may vary depending of program volume and number of claims needed to reach a representative sample. All Contract clinics will be subject to sampling reviews by CRR teams at least annually. Sampling will follow the same process described above. The report of findings will go to the supervisor and manager providing oversight to that contractor during technical assistance meetings with provider staff to discuss their review findings and corrective actions required. Follow up will be conducted to ensure all required modifications or recoupments are complete. | DMC-ODS- Annual monitoring for each network provider was conducted during FY 24-25. The overall compliance rate for the annual reviews was 92.2% MHP AOA conducted documentation chart reviews for 30 adult and older adult county/contracted programs. The pass rate for FY 24/25 was 94%. MHP CYS: Chart review data currently unavailable. |  | CRRT
Utilization Management (UM) | Ensure services claimed to Medi-Cal did occur. | Both | Percentage of Service Verification Surveys (SVS) that are returned to the County indicating that a claimed service did not occur. | A SVS process exist to ensure that services claimed to Medi-Cal did occur. Each CRR team is responsible for pulling random samples of services claimed monthly or quarterly, depending on the specific type of program, and the preparing surveys to be sent to members requesting a response if the claimed service identified on the survey did not occur. This is a negative reporting process in which no response is expected at all if the service in question occurred. Service Verification results will be analyzed and reported yearly. | The SVS process will consist of sampling of claimable services will be selected each month. A mailer will be sent to the member/parent/guardian offering an opportunity for the member/parent/guardian to contact QMS if the service did not occur and to provide some satisfaction information if the service did occur. This information is then analyzed and review at least annually with the CQIC. | In FY 24/25, AOA service area sent 457 surveys, CYS service area sent 151 surveys, and DMC service area sent 367 surveys. Of the surveys returned, AOA received 23 returns (5%); CYS received 5 (3%) and DMC had no returns. Due to the limited number of responses in each service area, average ratings on these questions were not analyzed. There were no reports that services did not occur; however, some surveys were returned with feedback. Due to the limited number of responses in each service area, average ratings on these questions were not analyzed. |  | DAE / CRRT
Utilization Management (UM) | Implementation of the SMHS Screening/Transition tool policy and related procedures. | SMHS | Publishing of County "MHP screening and transition" P&P and communication to network providers | In collaboration with Adult/Older Adult (AOA) and Children/Youth Services (CYS) administrative program staff, QMS staff will develop P&P and communication plans to ensure all network providers are aware of this policy. This metric will be measured by the presence of updated P&P and applicable notices/memos to providers. | The CalAIM "Screening and Transition" tool, aims to ensure all Medi-Cal members receive timely,coordinated services across Medi-Cal mental health delivery systems and improve member health outcomes. The goal is to ensure member access to the right care, in the right place, at the right time. The Screening and Transition of Care Tools for Medi-Cal Mental Health Services guide referrals to the Medi-Cal mental health delivery system (i.e., Medi-Cal Managed Care Health Plan (MCP) or BHP) that is expected to best support each member. Orange County Health Care Agency (OCHCA) adheres to this requirement and will collaborate with the county MCP to develop effective processes and to ensure appropriate tracking and reporting. This implementation will be complex and involve several County function areas, including Information Technology, BHS program staff, QMS at minimum, as well as the County MCP. | The Screening and Transition of Care tool data exchange and care coordination with CalOptima Health solution was implemented through Chorus during this year. As of the end of the FY, continuous improvement activities continue to streamline the process. The utilization of the Chorus solution by Kaiser Permanente is still in progress through ongoing coordination and data exchange agreements. |  | DAE / TATS

## Do Not Use
Accessibility of Services (ACC)
Utilization Management (UM)
Safety of Services / Clinical Care (SCC)
Member Satisfaction (MS)
Quality Assurance (QA)
Performance Improvement Projects (PIP)